## Master Data Sheet
Master Job Costing Sheet
Project Information | [6 empty] | Total Gross Profit |  |  | Total GPM |  |  | Total Labor GPM |  |  | Total Product GPM |  |  | Trim/Finish Total GPM |  |  | Rough Total GPM |  |  | Total Hours |  |  | Total PM Hours |  |  | Total Design Hours |  |  | Total Security Install Hours |  |  | Total Trim/Finish Install Hours |  |  | Rough Total Install Hours |  |  | Total Drive Time Hours | Total Wire Usage |  |  | Import Data
Summations
Project Name | Builder/Location | Project Manager | Department | Rough-in Completion Date | Finish Completion Date | Total Contract Value | Estimated Total Gross Profit | Actual Total Gross Profit | Total Gross Profit Difference | Estimated Total GPM | Actual Total GPM | Total GPM Difference | Estimated Total Labor GPM | Actual Total Labor GPM | Total Labor GPM Difference | Estimated Total Product GPM | Actual Total Product GPM | Total Product GPM Difference | Estimated Final Total GPM | Actual Final Total GPM | Final Total GPM Difference | Estimated Rough Total GPM | Actual Rough Total GPM | Total Rough GPM Difference | Estimated Total Hours | Actual Total Hours | Total Hours Difference | Estimated Total PM Hours | Actual Total PM Hours | Total PM Hours Difference | Estimated Total Design Hours | Actual Total Design Hours | Total Design Hours Difference | Estimated Total Security Hours | Actual Total Security Hours | Total Security Hours Difference | Estimated Total Finish Hours | Actual Total Finish Hours | Total Finish Hours Difference | Estimated Total Rough Hours | Actual Total Rough Hours | Total Rough Hours Difference | Total Drive Time Hours | Estimated Total Wire Usage | Actual Total Wire Usage | Total Wire Usage Difference | Imported By | Imported Date | File Directory
Lown Bull Ranch | OSM | John Valiton | Residential | 2018-08-01 | 2019-03-01 | 242771.66 | 110524.79 | 131484.333 | 20959.543 | 45.53% | 54.16% | 8.633% | 63.84% | 69.63% | 5.795% | 30.17% | 44.52% | 14.36% | 40.19% | 45.48% | 5.29% | 62.37% | 70.88% | 8.511% | 1151.56 | 894.64 | -256.92 | 147.025 | 191.5 | 44.475 | 104.089 | 47.67 | -56.419 | 222.638 | 200.46 | -22.178 | 472.469 | 326.43 | -146.039 | 196.339 | 119.81 | -76.529 | 112.63 | 23080 | 21256 | -1824 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Lown Ranch\Lown Bull Ranch Job Costing Dashboard.xlsm
Carey - YCC 2303 | GE Johnson | Cody Setzer | Commercial | N/A | 2019-03-01 | 107595.59 | 52097.62 | 43807.414 | -8290.206 | 48.42% | 40.71% | -7.705% | 61.14% | 43.73% | -17.41% | 41.38% | 39.04% | -2.336% | 49.95% | 40.38% | -9.569% | 0.5861% | 51.2% | 50.62% | 432 | 727.49 | 295.49 | 71.225 | 98.19 | 26.965 | 80.62 | 51.45 | -29.17 | 2 | 0 | -2 | 220.755 | 527.45 | 306.695 | 26.4 | 26.4 | 0 | 145.19 | 0 | 0 | 0 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\YC Core Condos\Condo 2303 Carey\Carey 2303 Job Costing.xlsx
YC Lot 30 | PRG | Miles Curtis | Residential | 2018-10-01 | 2019-04-01 | 149460.6 | 68346.34 | 69727.88 | 1381.54 | 45.73% | 46.65% | 0.9244% | 59.87% | 52.02% | -7.846% | 37.4% | 43.49% | 6.09% | 44.58% | 50.06% | 5.483% | 74.13% | -37.83% | -112% | 607.269 | 819.63 | 212.361 | 99.74 | 197.85 | 98.11 | 38.046 | 56.05 | 18.004 | 66.758 | 118.72 | 51.962 | 351.385 | 285.94 | -65.445 | 19.5 | 158.57 | 139.07 | 143.01 | 1000 | 11297 | 10297 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\YC Lot 30\YC Lot 30 Job Costing Dashboard.xlsx
Bruder - YCC 2-203 | GE Johnson | Mike Parks | Commercial | N/A | 2019-05-01 | 80178.95 | 30037.07 | 17191.505 | -12845.565 | 37.46% | 21.44% | -16.02% | 53.06% | 21.26% | -31.8% | 29.9% | 21.53% | -8.373% | 37.18% | 19.57% | -17.61% | 44.13% | 66.09% | 21.97% | 350.815 | 686.99 | 336.175 | 60.425 | 61.32 | 0.895 | 56.72 | 40.05 | -16.67 | 0 | 1.28 | 1.28 | 203.67 | 561.46 | 357.79 | 16.5 | 16.5 | 0 | 228.25 | 0 | 0 | 0 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\YC Core Condos\Condo 2203 Bruder\Bruder_Job Costing.xlsm
Riley AV Upgrade | N/A | Kolby Bruns | Client Services | N/A | 2019-06-01 | 48637.54 | 20927.99 | 23051.41 | 2123.42 | 44.67% | 47.39% | 2.721% | 53.8% | 65.23% | 11.43% | 41.37% | 39.71% | -1.661% | 44.67% | 47.39% | 2.721% | #DIV/0! | #DIV/0! | #DIV/0! | 102.27 | 169.82 | 67.55 | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 62.27 | 146.82 | 84.55 | 0 | 0 | 0 | 45.55 | 0 | 0 | 0 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Riley\Riley_Job Costing.xlsm
Kayden YC 717 | PRG | Nels Tate | Residential | 2018-09-01 | 2019-06-01 | 137831.48 | 64007.73 | 46999.406 | -17008.324 | 46.44% | 34.1% | -12.34% | 50.12% | 22.78% | -27.34% | 44.37% | 40.48% | -3.886% | 41.34% | 28.59% | -12.74% | 60.22% | 48.97% | -11.25% | 678.556 | 1310.67 | 632.114 | 89.104 | 186.75 | 97.646 | 67.02 | 93.6 | 26.58 | 127.396 | 204.04 | 76.644 | 208.286 | 369.11 | 160.824 | 159.75 | 457.17 | 297.42 | 287.17 | 16850 | 22130 | 5280 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Kayden_YC 717\Kayden YC 717 Job Costing Dashboard.xlsx
Vassilatos Chalet 15 | Highline Partners | John Valiton | Residential | N/A | 2019-08-01 | 248560.9 | 113427.73 | 102408.123 | -11019.607 | 45.63% | 41.2% | -4.433% | 58.88% | 24.25% | -34.63% | 41.31% | 46.73% | 5.419% | 41.96% | 37.75% | -4.21% | 65.44% | 59.8% | -5.639% | 799.043 | 1299.86 | 500.817 | 103.194 | 312.33 | 209.136 | 66.762 | 73.35 | 6.588 | 54.016 | 44.23 | -9.786 | 313.196 | 530.79 | 217.594 | 203.625 | 339.16 | 135.535 | 256.38 | 17950 | 16516 | -1434 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Vassilatos_Chalet 15\Vassilatos_Chalet 15 Job Costing Dashboard.xlsm
Maxwell Lyons - 4-402 | GE Johnson | Bryce Staker | Commercial | N/A | 2019-10-01 | 140598.23 | 67608.11 | 71709.534 | 4101.424 | 48.09% | 51% | 2.917% | 59.93% | 57.87% | -2.062% | 42.2% | 47.59% | 5.39% | 47.26% | 50.48% | 3.223% | 70.03% | 64.87% | -5.161% | 476.399 | 616.35 | 139.951 | 64.801 | 52.51 | -12.291 | 71.716 | 59.38 | -12.336 | 0 | 0 | 0 | 283.132 | 449.73 | 166.598 | 25.5 | 25.5 | 0 | 139.87 | 0 | 0 | 0 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\YC Core Condos\Condo 4402 Maxwell-Lyons\Maxwell Lyons 4402 Job Costing.xlsm
Tharaldson - RH3B | PRG | KC Chvilicek | Residential | 2019-05-01 | 2019-10-31 | 249209.66 | 109696.78 | 97159.424 | -12537.356 | 44.02% | 38.99% | -5.031% | 46.98% | 28.43% | -18.55% | 42.54% | 44.23% | 1.689% | 45.43% | 34.89% | -10.54% | 30.87% | 77.22% | 46.35% | 858.681 | 834.25 | -24.431 | 112.015 | 237.75 | 125.735 | 76.183 | 66.65 | -9.533 | 62.751 | 160.06 | 97.309 | 484.812 | 365.49 | -119.322 | 7.5 | 4.3 | -3.2 | 140.44 | 21411 | 20634 | -777 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Tharaldson_River Homestead 3B\Tharaldson_RH3B Job Costing Dashboard.xlsm
Bramley YC 422 | SBC | KC Chvilicek | Residential | 2019-06-01 | 2019-12-01 | 306861.02 | 143918.31 | 120687.58 | -23230.73 | 46.9% | 39.33% | -7.57% | 56.07% | 41.19% | -14.88% | 42.03% | 38.34% | -3.687% | 42.44% | 34.59% | -7.854% | 64.03% | 57.55% | -6.48% | 1343.482 | 2278.14 | 934.658 | 199.491 | 493.5 | 294.009 | 111.878 | 206.52 | 94.642 | 136.254 | 280.42 | 144.166 | 536.829 | 742.58 | 205.751 | 313.53 | 547.3 | 233.77 | 429.92 | 25325 | 35776 | 10451 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Bramley-Don_YC_Lot_422\Bramley YC 422 Job Costing Dashboard.xlsm
Stahl YC Lot 720 | PRG | KC Chvilicek | Residential | 2019-08-01 | 2019-12-01 | 192748.02 | 80263.69 | 57303.094 | -22960.596 | 41.64% | 29.73% | -11.91% | 38.69% | 12.68% | -26% | 42.84% | 36.66% | -6.179% | 35.54% | 19.46% | -16.08% | 60.05% | 60.72% | 0.6693% | 996.024 | 1608.36 | 612.336 | 160.784 | 337.74 | 176.956 | 95.554 | 162.35 | 66.796 | 163.801 | 160.33 | -3.471 | 316.245 | 567.81 | 251.565 | 253.14 | 373.55 | 120.41 | 291.61 | 23430 | 25320 | 1890 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Stahl YC 720\Stahl YC 720 Dashboard.xlsm
Highlands Cabins Lot 17 | PRG | Paul Bentley | Residential | N/A | 2019-12-20 | 26988.48 | 12634.17 | 11707.87 | -926.3 | 46.81% | 43.38% | -3.432% | 67.6% | 47.5% | -20.1% | 37.99% | 41.77% | 3.781% | 46.81% | 42.97% | -3.841% | #DIV/0! | 66.39% | #DIV/0! | 75.043 | 95.79 | 20.747 | 9.782 | 34.5 | 24.718 | 6.656 | 0 | -6.656 | 1.5 | 0 | -1.5 | 57.105 | 61.29 | 4.185 | 0 | 0 | 0 | 16.27 | 0 | 0 | 0 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Highlands Cabins Lot 17\Highlands Cabins Lot 17 Job Costing Dashboard.xlsm
Hilzinger YC Lot 99 | OSM | Eric Staker | Residential | 2019-10-31 | N/A | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 307.532 | 350.59 | 43.058 | 135.367 | 153 | 17.633 | 92.155 | 0 | -92.155 | 18.522 | 20.81 | 2.288 | 0 | 0 | 0 | 61.488 | 176.78 | 115.292 | 92.7665 | 59669 | 54526 | -5143 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Hilzinger_YC Lot 99\Hilzinger_Lot 99 Job Costing Dashboard.xlsx
Myrhvold AS 872 | PRG | Brent Vickland | Residential | 2019-11-01 | N/A | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 349.852 | 734.3333 | 384.4813 | 45.559 | 251.5 | 205.941 | 30.948 | 10.22 | -20.728 | 72.174 | 110.8133 | 38.6393 | 0 | 0 | 0 | 201.171 | 361.8 | 160.629 | 178.7833 | 21416 | 25898 | 4482 | Julian.Kizanis | 2020-02-06 | C:\Users\{user}\SAV Digital Environments\SAV - Documents\Departments\Accounting\Job Costing\Myrhvold_AS 872\Myrhvold_AS872 Job Costing Dashboard.xlsx